## pg1
| Asset | Task | DUE DATE | Priority | Status | Comments/Additional Info
Design/Character | Prof D | Abilities | 2022-02-21 | High | Done
Design/Character | Starship | Abilities | 2022-02-21 | High | Done
Design/Character | Sarah & Loki | Abilities | 2022-02-21 | High | Done
Design/Character | Gary M Unger | Abilities | 2022-02-21 | High | Done
Production | Asset List | Begin adding tasks to asset list and JIRA | 2022-02-28 | High | Done
Production | Asset List | Compile list of assets critical to Demo Build | 2022-03-07 | Highest | Done
Design/Level | Construction | Concept/Draft | 2022-03-07 | Low | Done
Design/Level | Frozen Pond | Concept/Draft | 2022-03-07 | Low | Done
Design/Level | Mason Circle | Concept/Draft | 2022-03-07 | Low | Done
Design/Level | Sarah's Lab | Concept/Draft | 2022-03-07 | Low | Done
Design/Level | Room 1018 | Concept/Draft | 2022-03-07 | Low | Done
Design/Level | Teleportartion Lab | Concept/Draft | 2022-03-07 | Low | Done
Production | Asset List | Discuss E3 Build expectations and plan of action upon return from spring break. Determine who will be presenting. | 2022-03-14 | Medium | Done
Programming | Starship | Abilities | 2022-03-14 | High | Done
Programming | Sarah | Abilities | 2022-03-14 | High | Done
Art/Character | Starship | UVs & Rigging | 2022-03-14 | Highest | Done
Art/Character | Sarah & Loki | UVs & Rigging | 2022-03-14 | Highest | Done
Production | Asset List | SPRING BREAK (Optional Week) | 2022-03-21 | Low | Done
Programming | Sarah | Model in-game | 2022-03-21 | High | Done
Programming | Starship | Model in-game | 2022-03-21 | High | Done
Production | Asset List | Demo Build Week (Update docs) | 2022-03-28 | Lowest | Done
Marketing | Social Media | Instagram Page | 2022-03-28 | Low | Done
Programming | UI | Main Menu | 2022-03-28 | High | Done
Programming | UI | Pause Menu | 2022-03-28 | Medium | Done
Programming | UI | Gameplay | 2022-03-28 | Highest | Done
Programming | Sarah | Animations in-game | 2022-03-28 | High | Done
Programming | Starship | Animations in-game | 2022-03-28 | High | Done
Programming | Build | Demo/Prototype | 2022-03-28 | Highest | Done
Sound/Music | Main Menu | Theme | 2022-03-28 | Medium | Done
Sound/Music | Character Select | Theme | 2022-03-28 | High | Done
Sound/Music | Construction | Theme | 2022-03-28 | Highest | Done
Production | Asset List | Update Asset list | 2022-04-18 | Lowest | Done
Sound/SFX | Starship | Disk Interactions (Throw, Catch, etc.) | 2022-03-28 | Highest | Done
Art/Character | Starship | Model | 2022-03-28 | Highest | Done
Art/Character | Sarah & Loki | Model | 2022-03-28 | Highest | Done
Sound/SFX | Starship | Abilities SFX | 2022-03-28 | High | Done
Sound/SFX | Starship | Additional SFX (Not movement or abilities) | 2022-03-28 | Medium | Done
Production | Asset List | Asset List updates | 2022-04-11 | Lowest | Done
Art/Character | Starship | Textures | 2022-03-28 | High | Done
Art/Character | Sarah & Loki | Textures | 2022-03-28 | High | Done
Art/Character | Starship | Animations | 2022-03-28 | Highest | Done
Art/Character | Sarah & Loki | Animations | 2022-03-28 | Highest | Done
Art/UI | Main Menu | Menu Art | 2022-03-28 | High | Done
Art/UI | Gameplay | In-Match Art (Timer, Score, etc.) | 2022-03-28 | Highest | Done
Art/Level | Construction | The Net: just the yellow caution tape that you see around | 2022-03-28 | Medium | Done
Art/Level | Construction | The black: assorted sinkholes, think brown with a mix of black coloring | 2022-03-28 | Medium | Done
Art/Level | Construction | Obstacles: assorted construction equipment, boxes, tools (hammers, drills, screwdrivers, saws) | 2022-03-28 | Medium | Done
Art/Level | Construction | Goals: assorted pieces of scaffolding. Prominent red tape to signify red score, prominent yellow tape to signify yellow score | 2022-03-28 | Highest | Done
Art/Level | Construction | Scoring: Scores are held up by construction workers at the top of the screen | 2022-03-28 | High | Done
Art/Level | Construction | Timer: Timer is done by one of those road warning lights that point arrows to merge over. | 2022-03-28 | High | Done
Art/Level | Construction | Audience: assorted construction workers watching chaos unfold | 2022-03-28 | Low | Done
Sound/SFX | Sarah & Loki | Disk Interactions (Throw, Catch, etc.) | 2022-03-28 | Highest | Done
Sound/SFX | Sarah & Loki | Abilities SFX | 2022-03-28 | High | Done
Sound/SFX | Sarah & Loki | Additional SFX (Not movement or abilities) | 2022-03-28 | Medium | Done
Production | Asset List | Ascertain what is doable with the remaining month from each team to determine what bottlenecks will/are occuring. | 2022-04-04 | Lowest | Done
Programming | Build | Demo/Prototype | 2022-04-02 | Highest | Done
Art/Character | Prof D | Model | 2022-04-04 | High | Done
Art/Character | Gary M Unger | Model | 2022-04-04 | Medium | Done
Art/Character | Prof D | UVs & Rigging | 2022-04-11 | High | Done
Art/UI | Menu | Buttons and Background Art | 2022-04-11 | Medium | Done
Sound/SFX | Construction | Level Related SFX (Jackhammers, etc.) | 2022-04-18 | Low | Done
Programming | Teleportartion Lab | Functional | 2022-04-13 | High | Done
Art/Character | Gary M Unger | UVs & Rigging | 2022-04-11 | Medium | Done
Sound/SFX | Starship | Movement Related SFX | 2022-04-18 | High | Done
Sound/SFX | Sarah & Loki | Movement Related SFX | 2022-04-18 | High | Done
Sound/Music | Teleportartion Lab | Theme | 2022-04-18 | Medium | Done
Sound/SFX | Prof D | Movement Related SFX | 2022-04-18 | High | Done
Sound/SFX | Prof D | Disk Interactions (Throw, Catch, etc.) | 2022-04-18 | Highest | Done
Sound/SFX | Prof D | Abilities SFX | 2022-04-18 | High | Done
Sound/SFX | Prof D | Additional SFX (Not movement or abilities) | 2022-04-18 | Medium | Done
Art/Level | Teleportartion Lab | Ground: ‘Caution Keep Out’ tapes, Green and Yellow Stars for scoring, little colored papers used in parties(idk the name of it) | 2022-04-18 | Medium | Done
Art/Level | Teleportartion Lab | Plain white walls for the lab, a light green stripe going around could look nice. | 2022-04-18 | Low | Done | Double check with design since the labs have now been merged
Art/Level | Teleportartion Lab | The Net | 2022-04-18 | Highest | Done | Double check with design since the labs have now been merged. "it can be as plain and simple or as Sci-Fi and extravagant as you want."
Art/Level | Teleportartion Lab | The Scoreboard: Power Generator | 2022-04-18 | High | Done | See doc for more details and reference images. "I imagine a sophisticated looking power generator inside of the lab working away at powering the ridiculous teleportation devices."
Art/Level | Teleportartion Lab | Teleporters | 2022-04-18 | High | Done | Docs have no information, check with design
Art/Level | Teleportartion Lab | Control Stations | 2022-04-18 | High | Done | See doc for more details and reference images. "basically techy big machines with glowing buttons and screens resembling a retro arcade machine"
Art/Level | Teleportartion Lab | Cables and Junk: | 2022-04-18 | Low | Done | "Random electric cables, cords, and other bits and pieces to be plastered all over the floors to add to the lab feel."
Art/Level | Teleportartion Lab | The Crowd | 2022-04-18 | High | Done | "Mini white robots are the crowds cheering on the top (some are waving flags)"
Programming | Gameplay | 4 player experiment | 2022-04-25 | Lowest | CUT
Programming | Teleportartion Lab | Playable with assets | 2022-04-25 | Highest | Done
Programming | Frozen Pond | Functional | 2022-04-18 | High | Done
Sound/SFX | Teleportartion Lab | Level Related SFX (teleporters, electronics, etc.) | 2022-04-25 | Low | Done | check with design since this has been merged with Sarah's lab
Art/Level | Teleportartion Lab | A robot referee | 2022-04-18 | Medium | Done
Sound/Music | Frozen Pond | Theme | 2022-04-25 | Medium | Done
Production | Asset List | Discuss stretch goals, 4 players, etc. | 2022-04-25 | Lowest | Done
Sound/SFX | Gary M Unger | Movement Related SFX | 2022-04-25 | High | Done
Sound/SFX | Gary M Unger | Abilities SFX | 2022-04-25 | High | Done
Sound/SFX | Gary M Unger | Disk Interactions (Throw, Catch, etc.) | 2022-04-25 | Highest | Done
Sound/SFX | Gary M Unger | Additional SFX (Not movement or abilities) | 2022-04-25 | Medium | Done
Art/Character | Prof D | Animations | 2022-04-25 | High | Done
Art/Character | Prof D | Textures | 2022-04-25 | High | Done
Art/Character | Gary M Unger | Textures | 2022-04-25 | Medium | Done
Art/Level | Frozen Pond | Goose modeled and textured | 2022-04-25 | High | In-progress
Art/Character | Gary M Unger | Animations | 2022-04-25 | Medium | Done
Art/Level | Frozen Pond | Snow piles | 2022-04-25 | High | Done
Art/Level | Frozen Pond | Ice floor | 2022-04-25 | Medium | Done
Sound/SFX | Frozen Pond | Level Related SFX (Goose, etc.) | 2022-04-25 | Low | Done
Marketing | Social Media | Screenshots | 2022-05-02 | Low | To-Do
Programming | Frozen Pond | Playable with assets | 2022-05-02 | Highest | To-Do
Programming | Menu | Proper Options menu | 2022-05-02 | Lowest | CUT | Talk to Kyle
Marketing | Itch | Itch.io page with description | 2022-05-02 | Highest | To-Do
Production | Asset List | Senior Expo Build Preparation & AL update | 2022-05-02 | Lowest | To-Do
Programming | Main Menu | Credits | 2022-05-02 | Low | To-Do | Simple Credits reel
Art/Level | Mason Circle | Mason Statue | 2022-05-02 | Lowest | CUT
Art/Level | Mason Circle | Floor | 2022-05-02 | Lowest | CUT | "Style-appropriate rendition of George Mason at center, ground looks like the area around the GM Statue by the Johnson Center, statue on bottom"
Art/Level | Mason Circle | Crowd | 2022-05-02 | Lowest | CUT
Art/Level | Mason Circle | Goals | 2022-05-02 | Lowest | CUT
Programming | Build | Senior Expo Build | 2022-05-04 | Highest | In-progress
Marketing | Social Media | Trailer/Gameplay vid | 2022-05-09 | Medium | To-Do
Marketing | Social Media | Final Progress Update/Post | 2022-05-16 | Medium | To-Do
Production | Asset List | Polish, should be final asset list update | 2022-05-09 | Lowest | To-Do
Programming | Build | Polish and Bug squashing | 2022-05-09 | Highest | To-Do
Programming | Build | Further polish and ensuring winnitron & itch.io versions work. | 2022-05-16 | Highest | To-Do | This is the absolute final turn in Due @1:30pm.