## Sheet1
Sprint | GOALS | Due Date | Notes/Comments
1 | Theme, Art Style | 2022-02-07 | Art style should be established as well as overall theme narrowed down
2 | Music, Character(s) | 2022-02-14 | Music should be on path to establish general mood. 1st Character needs to be designed or near done
3 | Lvl1 | 2022-02-21 | Want to see a prototype of lvl 1 even if it's just design docs
4 | Character 1 in-game | 2022-02-28 | All character models nearly finished
5 | Character Model(s) | 2022-03-07 | Character UVs done, some rigging. Determine scale
6 | Title | 2022-03-14 | SPRING BREAK, Prof said we can have a bonus (optional) sprint this week
EX | Catch-up | 2022-03-21 | Starship & Prof D should be done by the time of the Prototype/demo. Base Gameplay is complete
7 | Prototype/Demo | 2022-03-28 | Polish will be done this week, game will be presented on April 3rd
8 | Cleaned up assets | 2022-04-04 | Juicing for design team, everyone else focuses on moving to next levels, cleaning up sfx, etc.
9 | Clean Up & Reorganizing | 2022-04-11 | Clean up assets from the "E3 Build"
10 | Lab level | 2022-04-18 | Level is playable with most of its assets ready to be or already added in the game.
11 | All assets are done | 2022-04-25 | Level is playable. Animations finished on remaining characters
12 | Senior Expo Build | 2022-05-02 | Really want a finished build by this week so we can focus on itch.io deployment and polish
13 | All polished assets done | 2022-05-09 | Make sure the Winnitron and Itch page are working properly
14 | Publish | 2022-05-16 | Final Build Submission inculding deployment due @1:30pm
LAST 2 WEEKS:
|  | 2022-04-25 | ART & SOUND: Most if not all of the remaining assets should be done and teams should transition to polish and promo material
|  | 2022-05-01 | DEADLINE: No new assets past this point
|  | 2022-05-02 | PROG: Senior expo build presented in-class. Ideally DESIGN can playtest it on Winnitron
|  | 2022-05-04 | PROG: Ensure Senior Expo build is presentable and ready to show off by this date. Again there should be a playable build for DESIGN on the Winnitron.
|  | 2022-05-05 | SENIOR EXPO
|  | 2022-05-09 | Last day to submit polished assets. Anything past this point is up to PROG if it goes into the build; however, Jon and I have veto power